## Portfolio
Issue Key | Issue Type | Project Name | Task / Summary | Phase | Owner | Team | Resources Needed | Priority | Status | Start Date | Baseline Due Date | Due Date (Current) | Days Slipped | RAG Status | % Complete | Effort (Days) | Dependencies | Governance Level | Known Issues / Bugs | Issue Severity | Last Updated | Notes | Next Step / Recommended Action
META-RRO-0 | Epic | Reels Ranking Overhaul | Improve Reels session time and creator retention via a new multi-task ranking model | Full Marketable Solution | Elena Vasquez | Ranking & Recommendations | 2 ML Engineers, 1 Data Scientist, 1 Eng Manager, 1 PM | High | At Risk | 2026-01-05 | 2026-08-31 | 2026-09-30 | 30 | Red | 81 |  |  | Steering Committee Review | 1 critical/high severity issue(s) open across sub-tasks | Critical | 2026-08-15 | Flagship ranking refresh for FY26; feeds Creator Monetization Suite | Escalate infra scaling fix (RRO-5) to unblock deployment ramp; portfolio review recommended.
META-RRO-1 | Sub-task | Reels Ranking Overhaul | Audit current ranking model bottlenecks | Prototype Design | Marcus Lee | Ranking & Recommendations | - | High | Done | 2026-01-05 | 2026-01-30 | 2026-01-30 | 0 | Green | 100 | 15 |  |  | No known issues | None | 2026-01-29 | Identified latency in candidate generation stage | No action needed — delivered.
META-RRO-2 | Sub-task | Reels Ranking Overhaul | Build multi-task ranking prototype (v0) | Prototype Design | Marcus Lee | Ranking & Recommendations | - | High | Done | 2026-02-02 | 2026-03-13 | 2026-03-13 | 0 | Green | 100 | 30 | META-RRO-1 |  | No known issues | None | 2026-03-12 | Prototype validated offline on holdout set | No action needed — delivered.
META-RRO-3 | Sub-task | Reels Ranking Overhaul | Train MVP ranking model on 90-day engagement data | MVP | Priya Anand | Ranking & Recommendations | - | High | Done | 2026-03-16 | 2026-04-10 | 2026-04-24 | 14 | Amber | 100 | 28 | META-RRO-2 |  | No known issues | None | 2026-04-23 | Model beat baseline by 4.2% offline NDCG; delivered 2 weeks late | No further action; note recurring 2-week slip pattern for retro.
META-RRO-4 | Sub-task | Reels Ranking Overhaul | Run sandbox A/B test on 2% of traffic | Sandbox Testing | Priya Anand | Ranking & Recommendations | - | High | Done | 2026-04-27 | 2026-06-05 | 2026-06-05 | 0 | Green | 100 | 28 | META-RRO-3 |  | No known issues | None | 2026-06-04 | Result: +3.1% session time, greenlit for deployment ramp | No action needed — delivered.
META-RRO-5 | Sub-task | Reels Ranking Overhaul | Deployment testing at 25% traffic ramp | Deployment Testing | Marcus Lee | Ranking & Recommendations | - | High | At Risk | 2026-06-08 | 2026-07-10 | 2026-07-31 | 21 | Red | 65 | 35 | META-RRO-4 |  | 3 open defects: candidate-generation service p95 latency spikes to 220ms under peak load (RRO-BUG-101/102/103) | Critical | 2026-08-14 | Candidate-generation service under-provisioned at peak load; overdue | Get Infra on-call to size candidate-gen capacity this week; re-baseline date.
META-RRO-6 | Sub-task | Reels Ranking Overhaul | Post-production monitoring & guardrail tuning | Post-Production Testing | Elena Vasquez | Ranking & Recommendations | - | Medium | Blocked | 2026-08-03 | 2026-09-05 | 2026-09-30 | 25 | Red | 20 | 25 | META-RRO-5 |  | No new defects logged yet; blocked before guardrail tuning could begin | None | 2026-08-15 | Blocked pending infra fix from META-RRO-5 | Cannot start guardrail tuning until RRO-5 clears; track as dependency risk.
META-LEAP-0 | Epic | Llama Enterprise API Platform | Hosted, SLA-backed API for Llama models with billing, quotas and fine-tuning for enterprise customers | Full Marketable Solution | David Kim | Generative AI Platform | 3 Backend Engineers, 1 SRE, 1 Solutions Architect, 1 PM | High | At Risk | 2026-01-12 | 2026-10-15 | 2026-11-30 | 46 | Red | 65 |  | META-DCE-0 | Steering Committee Review | 1 lower-severity issue(s) resolved, none currently open | Low | 2026-08-15 | GA target Q4 FY26; capacity depends on Data Center Efficiency program | Confirm GPU capacity commitment from Infra by end of month or pull in contingency plan.
META-LEAP-1 | Sub-task | Llama Enterprise API Platform | Define enterprise API requirements & SLAs | End-to-end Design | Sofia Marin | Generative AI Platform | - | High | Done | 2026-01-12 | 2026-02-13 | 2026-02-13 | 0 | Green | 100 | 22 |  |  | No known issues | None | 2026-02-12 | SLA tiers agreed with 3 design-partner customers | No action needed — delivered.
META-LEAP-2 | Sub-task | Llama Enterprise API Platform | Build POC: single-tenant inference endpoint | POC | Sofia Marin | Generative AI Platform | - | High | Done | 2026-02-16 | 2026-03-27 | 2026-03-27 | 0 | Green | 100 | 30 | META-LEAP-1 |  | No known issues | None | 2026-03-26 | POC met p95 latency target of 800ms | No action needed — delivered.
META-LEAP-3 | Sub-task | Llama Enterprise API Platform | Design multi-tenant billing & quota architecture | End-to-end Design | Rahul Sethi | Generative AI Platform | - | Medium | Done | 2026-03-30 | 2026-04-24 | 2026-04-24 | 0 | Green | 100 | 18 | META-LEAP-2 |  | No known issues | None | 2026-04-23 | Usage-based billing model approved by Finance | No action needed — delivered.
META-LEAP-4 | Sub-task | Llama Enterprise API Platform | Develop MVP hosted API with fine-tuning support | MVP | Rahul Sethi | Generative AI Platform | - | High | Done | 2026-04-27 | 2026-07-17 | 2026-07-17 | 0 | Green | 100 | 55 | META-LEAP-3 |  | 2 bugs found and fixed during integration testing (fine-tuning job retry logic) | Low | 2026-07-16 | Fine-tuning pipeline integrated and validated; handed to sandbox testing | No action needed — delivered.
META-LEAP-5 | Sub-task | Llama Enterprise API Platform | Provision GPU capacity via Data Center Efficiency program | Development | David Kim | Generative AI Platform | - | High | At Risk | 2026-06-01 | 2026-07-25 | 2026-08-28 | 34 | Red | 55 | 40 | META-DCE-3 |  | No software defects; blocked by external GPU capacity delivery, not a bug | None | 2026-08-14 | Delayed by cooling retrofit schedule slip | Escalate to DCE program owner for firm capacity delivery date; evaluate cloud burst as fallback.
META-LEAP-6 | Sub-task | Llama Enterprise API Platform | Sandbox testing with 5 pilot enterprise customers | Sandbox Testing | Sofia Marin | Generative AI Platform | - | High | Planning | 2026-08-31 | 2026-10-09 | 2026-10-09 | 0 | Green | 0 | 28 | META-LEAP-4, META-LEAP-5 |  | No known issues | None | 2026-08-15 | Pilot cohort confirmed, NDAs signed | Confirm LEAP-5 capacity lands before Aug 31 start; else slip start date.
META-LEAP-7 | Sub-task | Llama Enterprise API Platform | Deployment & post-production testing, GA rollout | Deployment Testing | David Kim | Generative AI Platform | - | Medium | Planning | 2026-10-12 | 2026-11-30 | 2026-11-30 | 0 | Green | 0 | 30 | META-LEAP-6 |  | No known issues | None | 2026-08-15 | GA readiness review scheduled for late Nov | On track to start as scheduled; confirm readiness review invite sent.
META-QMR-0 | Epic | Quest Mixed Reality OS Upgrade | Next-gen passthrough rendering and persistent spatial anchors for the Quest hardware line | MVP | Naomi Clarke | Reality Labs OS | 4 Systems Engineers, 2 Graphics Engineers, 1 QA Lead, 1 PM | High | On Track | 2026-01-19 | 2026-12-18 | 2026-12-18 | 0 | Green | 62 |  |  | Team-Level Tracking | 1 critical/high severity issue(s) open across sub-tasks | Critical | 2026-08-15 | Foundational OS update ahead of next hardware refresh; healthiest program in portfolio | Continue monitoring; no escalation needed.
META-QMR-1 | Sub-task | Quest Mixed Reality OS Upgrade | Prototype improved passthrough rendering pipeline | Prototype Design | Liam Osei | Reality Labs OS | - | High | Done | 2026-01-19 | 2026-03-06 | 2026-03-06 | 0 | Green | 100 | 33 |  |  | No known issues | None | 2026-03-05 | Reduced passthrough latency by 18ms | No action needed — delivered.
META-QMR-2 | Sub-task | Quest Mixed Reality OS Upgrade | Prototype persistent spatial anchor system | Prototype Design | Liam Osei | Reality Labs OS | - | High | Done | 2026-03-09 | 2026-04-17 | 2026-04-17 | 0 | Green | 100 | 28 | META-QMR-1 |  | No known issues | None | 2026-04-16 | Anchors persist across app restarts in lab tests | No action needed — delivered.
META-QMR-3 | Sub-task | Quest Mixed Reality OS Upgrade | Build POC: anchor sync across multi-user sessions | POC | Grace Tanaka | Reality Labs OS | - | Medium | Done | 2026-04-20 | 2026-06-12 | 2026-06-12 | 0 | Green | 100 | 38 | META-QMR-2 |  | 2 minor sync bugs in multi-user anchor merge, patched before sign-off | Low | 2026-06-11 | Sync validated for up to 4 concurrent users; POC accepted | No action needed — delivered.
META-QMR-4 | Sub-task | Quest Mixed Reality OS Upgrade | Develop MVP OS build for internal dogfood | MVP | Grace Tanaka | Reality Labs OS | - | High | On Track | 2026-06-15 | 2026-08-28 | 2026-08-28 | 0 | Green | 70 | 50 | META-QMR-3 |  | 1 critical crash bug on Quest 3 hardware during dogfood; hotfix in progress (QMR-BUG-201) | Critical | 2026-08-13 | Dogfood rollout to 500 employees begins this week | Continue monitoring; no escalation needed.
META-QMR-5 | Sub-task | Quest Mixed Reality OS Upgrade | Sandbox testing across Quest 3 & Quest 4 hardware | Sandbox Testing | Liam Osei | Reality Labs OS | - | High | Planning | 2026-08-31 | 2026-10-23 | 2026-10-23 | 0 | Green | 0 | 35 | META-QMR-4 |  | No known issues | None | 2026-08-15 | Device lab reserved for extended soak testing | On track to start as scheduled; confirm device lab booking.
META-QMR-6 | Sub-task | Quest Mixed Reality OS Upgrade | Full marketable solution certification & store release | Full Marketable Solution | Naomi Clarke | Reality Labs OS | - | Medium | Planning | 2026-10-26 | 2026-12-18 | 2026-12-18 | 0 | Green | 0 | 40 | META-QMR-5 |  | No known issues | None | 2026-08-15 | Store certification checklist drafted | On track to start as scheduled; no action needed yet.
META-UMB-0 | Epic | Unified Messaging Backend | Consolidate Messenger, Instagram DM and WhatsApp Business messaging onto one shared backend | Development | Carlos Mendez | Messaging Platform Infra | 3 Backend Engineers, 1 Security Engineer, 1 PM | High | Blocked | 2026-02-02 | 2026-09-01 | 2026-10-16 | 45 | Red | 62 |  |  | Steering Committee Review | 1 critical/high severity issue(s) open across sub-tasks | Critical | 2026-08-15 | Unlocks cross-app enforcement for Teen Safety & Wellbeing Controls | Compliance to fast-track WhatsApp bridge review; program blocking two downstream epics.
META-UMB-1 | Sub-task | Unified Messaging Backend | End-to-end design of unified message schema | End-to-end Design | Hana Suzuki | Messaging Platform Infra | - | High | Done | 2026-02-02 | 2026-03-20 | 2026-03-20 | 0 | Green | 100 | 32 |  |  | No known issues | None | 2026-03-19 | Schema supports all three surfaces without app-specific branching | No action needed — delivered.
META-UMB-2 | Sub-task | Unified Messaging Backend | Design cross-app identity & encryption mapping | End-to-end Design | Hana Suzuki | Messaging Platform Infra | - | High | Done | 2026-03-23 | 2026-04-24 | 2026-04-24 | 0 | Green | 100 | 25 | META-UMB-1 |  | No known issues | None | 2026-04-23 | Reviewed and signed off by Security team | No action needed — delivered.
META-UMB-3 | Sub-task | Unified Messaging Backend | Develop core routing service (Messenger + IG DM) | Development | Omar Farouk | Messaging Platform Infra | - | High | Done | 2026-04-27 | 2026-07-10 | 2026-07-10 | 0 | Green | 100 | 52 | META-UMB-2 |  | 4 routing bugs resolved prior to sign-off (message ordering edge cases) | Medium | 2026-07-09 | Routing validated in staging for both surfaces; production-ready | No action needed — delivered.
META-UMB-4 | Sub-task | Unified Messaging Backend | Develop WhatsApp Business API bridge | Development | Omar Farouk | Messaging Platform Infra | - | High | At Risk | 2026-07-13 | 2026-08-25 | 2026-09-11 | 17 | Red | 60 | 42 | META-UMB-3 |  | 2 critical bugs in WhatsApp delivery-receipt handling, under investigation (UMB-BUG-310/311) | Critical | 2026-08-14 | WhatsApp compliance review adding a 2-week delay | Request expedited compliance review slot this sprint.
META-UMB-5 | Sub-task | Unified Messaging Backend | Deployment testing under peak concurrent load | Deployment Testing | Carlos Mendez | Messaging Platform Infra | - | High | Blocked | 2026-09-14 | 2026-09-20 | 2026-10-16 | 26 | Red | 10 | 25 | META-UMB-4 |  | No new defects logged; blocked pending UMB-4 fixes | None | 2026-08-15 | Blocked pending WhatsApp bridge completion | Cannot start until UMB-4 clears compliance; hold resourcing.
META-UMB-6 | Sub-task | Unified Messaging Backend | Post-production monitoring & rollback plan | Post-Production Testing | Hana Suzuki | Messaging Platform Infra | - | Medium | Planning | 2026-10-19 | 2026-11-13 | 2026-11-13 | 0 | Green | 0 | 15 | META-UMB-5 |  | No known issues | None | 2026-08-15 | Rollback runbook drafted, pending final review | On track to start as scheduled, contingent on UMB-5.
META-TSW-0 | Epic | Teen Safety & Wellbeing Controls | Age-appropriate defaults, parental controls and screen-time nudges across the family of apps | Development | Fatima Al-Rashid | Trust & Safety - Youth Products | 2 Backend Engineers, 1 Policy Specialist, 1 UX Researcher, 1 PM | High | At Risk | 2026-03-02 | 2026-10-01 | 2026-11-06 | 36 | Red | 52 |  | META-UMB-0 | Steering Committee Review | 1 critical/high severity issue(s) open across sub-tasks | Critical | 2026-08-15 | Compliance-driven program with hard regulatory deadline | Flag regulatory deadline risk to Legal now; contingency plan needed if UMB stays blocked past Sept.
META-TSW-1 | Sub-task | Teen Safety & Wellbeing Controls | Regulatory & policy requirements mapping | End-to-end Design | Ben Okafor | Trust & Safety - Youth Products | - | High | Done | 2026-03-02 | 2026-04-10 | 2026-04-10 | 0 | Green | 100 | 27 |  |  | No known issues | None | 2026-04-09 | Mapped requirements across US, EU and UK jurisdictions | No action needed — delivered.
META-TSW-2 | Sub-task | Teen Safety & Wellbeing Controls | Prototype parental control dashboard | Prototype Design | Ben Okafor | Trust & Safety - Youth Products | - | Medium | Done | 2026-04-13 | 2026-05-22 | 2026-05-22 | 0 | Green | 100 | 28 | META-TSW-1 |  | No known issues | None | 2026-05-21 | Usability tested with 12 parent households | No action needed — delivered.
META-TSW-3 | Sub-task | Teen Safety & Wellbeing Controls | Build cross-app enforcement hooks on unified backend | Development | Ines Duarte | Trust & Safety - Youth Products | - | High | Blocked | 2026-05-25 | 2026-07-25 | 2026-08-14 | 20 | Red | 45 | 45 | META-UMB-3 |  | 1 critical bug: enforcement hook crashes on cross-app identity mismatch (TSW-BUG-401) | Critical | 2026-08-14 | Waiting on unified routing service stability; overdue | Re-sequence against UMB-4 fix; consider interim per-app enforcement as stopgap.
META-TSW-4 | Sub-task | Teen Safety & Wellbeing Controls | Sandbox testing with teen accounts panel | Sandbox Testing | Ines Duarte | Trust & Safety - Youth Products | - | High | At Risk | 2026-08-17 | 2026-09-10 | 2026-09-25 | 15 | Red | 15 | 25 | META-TSW-3 |  | No new defects; testing paused pending TSW-3 fix | None | 2026-08-15 | Consent process finalized, but predecessor TSW-3 is blocked | Do not start until TSW-3 unblocks; hold panel schedule for now.
META-TSW-5 | Sub-task | Teen Safety & Wellbeing Controls | Post-production testing & compliance sign-off | Post-Production Testing | Fatima Al-Rashid | Trust & Safety - Youth Products | - | High | Planning | 2026-09-28 | 2026-11-06 | 2026-11-06 | 0 | Green | 0 | 22 | META-TSW-4 |  | No known issues | None | 2026-08-15 | Legal sign-off required before regional rollout | Monitor upstream slip; regulatory deadline has little buffer left.
META-DCE-0 | Epic | Data Center Liquid Cooling Efficiency | Retrofit GPU clusters with direct liquid cooling to cut PUE and free capacity for AI workloads | Full Marketable Solution | Wei Zhang | Infrastructure & Data Centers | 2 Mechanical Engineers, 2 Data Center Technicians, 1 PM | Medium | At Risk | 2026-01-05 | 2026-08-25 | 2026-09-18 | 24 | Red | 68 |  |  | Program-Level Governance | No known issues across sub-tasks | None | 2026-08-15 | Capacity unlock feeds directly into Llama Enterprise API Platform | Vendor to confirm revised hardware delivery date this week; impacts LEAP GA timeline.
META-DCE-1 | Sub-task | Data Center Liquid Cooling Efficiency | Prototype liquid cooling manifold design | Prototype Design | Anders Lindqvist | Infrastructure & Data Centers | - | Medium | Done | 2026-01-05 | 2026-02-20 | 2026-02-20 | 0 | Green | 100 | 33 |  |  | No known issues | None | 2026-02-19 | Manifold design passed thermal stress testing | No action needed — delivered.
META-DCE-2 | Sub-task | Data Center Liquid Cooling Efficiency | POC retrofit on single rack row | POC | Anders Lindqvist | Infrastructure & Data Centers | - | Medium | Done | 2026-02-23 | 2026-04-10 | 2026-04-10 | 0 | Green | 100 | 33 | META-DCE-1 |  | No known issues | None | 2026-04-09 | PUE improved from 1.18 to 1.07 on pilot row | No action needed — delivered.
META-DCE-3 | Sub-task | Data Center Liquid Cooling Efficiency | Full data hall retrofit rollout | Full Marketable Solution | Wei Zhang | Infrastructure & Data Centers | - | High | At Risk | 2026-04-13 | 2026-07-24 | 2026-08-21 | 28 | Red | 70 | 60 | META-DCE-2 |  | No software defects; vendor hardware delivery delay, not a bug | None | 2026-08-14 | Vendor hardware delivery slipped by 3 weeks | Escalate to vendor account team; assess partial-row cutover to protect LEAP timeline.
META-DCE-4 | Sub-task | Data Center Liquid Cooling Efficiency | Deployment testing under full AI training load | Deployment Testing | Anders Lindqvist | Infrastructure & Data Centers | - | Medium | Planning | 2026-08-24 | 2026-09-18 | 2026-09-18 | 0 | Green | 0 | 18 | META-DCE-3 |  | No known issues | None | 2026-08-15 | Test plan aligned with GenAI Platform training calendar | Contingent on DCE-3; confirm start date once vendor delivery firms up.
META-CMS-0 | Epic | Creator Monetization Suite | Bundle letting creators combine ads, subscriptions and tipping in one unified payout flow | MVP | Julia Novak | Monetization Products | 2 Backend Engineers, 1 Data Analyst, 1 PM | Medium | On Track | 2026-02-16 | 2026-10-30 | 2026-10-30 | 0 | Green | 73 |  | META-RRO-0 | Team-Level Tracking | 2 lower-severity issue(s) resolved, none currently open | Medium | 2026-08-15 | Uses Reels ranking signals to personalize monetization prompts | Continue monitoring; no escalation needed.
META-CMS-1 | Sub-task | Creator Monetization Suite | Design unified payout & revenue-share model | End-to-end Design | Sam Okoye | Monetization Products | - | Medium | Done | 2026-02-16 | 2026-03-27 | 2026-03-27 | 0 | Green | 100 | 27 |  |  | No known issues | None | 2026-03-26 | Revenue-share tiers approved by Finance & Legal | No action needed — delivered.
META-CMS-2 | Sub-task | Creator Monetization Suite | Prototype in-app monetization dashboard for creators | Prototype Design | Sam Okoye | Monetization Products | - | Medium | Done | 2026-03-30 | 2026-05-08 | 2026-05-08 | 0 | Green | 100 | 27 | META-CMS-1 |  | No known issues | None | 2026-05-07 | Tested with 20-creator advisory panel | No action needed — delivered.
META-CMS-3 | Sub-task | Creator Monetization Suite | Integrate ranking signals for personalized monetization tips | Development | Diego Alvarez | Monetization Products | - | Medium | Done | 2026-05-11 | 2026-07-24 | 2026-07-24 | 0 | Green | 100 | 44 | META-RRO-3 |  | 2 bugs found and fixed during ranking-signal integration testing | Low | 2026-07-23 | Ranking signal integration completed and validated | No action needed — delivered.
META-CMS-4 | Sub-task | Creator Monetization Suite | Build MVP payout flow with tax & compliance checks | MVP | Diego Alvarez | Monetization Products | - | High | On Track | 2026-07-27 | 2026-09-11 | 2026-09-11 | 0 | Green | 65 | 30 | META-CMS-3 |  | 1 medium bug in tax-withholding rounding logic, fix scheduled this sprint (CMS-BUG-501) | Medium | 2026-08-12 | Tax withholding logic validated for 6 pilot markets | Continue monitoring; no escalation needed.
META-CMS-5 | Sub-task | Creator Monetization Suite | Sandbox testing with 200-creator cohort | Sandbox Testing | Julia Novak | Monetization Products | - | Medium | Planning | 2026-09-14 | 2026-10-30 | 2026-10-30 | 0 | Green | 0 | 25 | META-CMS-4 |  | No known issues | None | 2026-08-15 | Cohort recruitment underway via Creator Studio | On track to start as scheduled; no action needed yet.
Notes:
RAG Status is derived: Red = Status is Blocked/At Risk; Amber = slipped past Baseline Due Date but not Blocked/At Risk; Green = on or ahead of baseline.
% Complete for Sub-tasks is manager-reported progress; Epic % Complete is the average of its Sub-tasks (formula-driven).
Known Issues / Bugs and Issue Severity are logged at Sub-task level; Epic-level values are formula rollups (counts of Critical/High severity items open across that project's Sub-tasks).
Governance Level is set at Epic level only, based on priority, RAG status, and cross-project dependency footprint.
Baseline Due Date reflects original committed plan; Due Date (Current) reflects latest re-forecast. All figures are illustrative/hypothetical.